## DRop 4 Loungewear
Style | Final Names | Shell Fabric + Color | Fabric status | Sizes | Factory | Final Qty | OG PO Delivery date | Remarks | FI date as on 13/04 | Delivery Date | Photoshoot sample update
SS23/WA/T739/Drop 5 | Gathered Jersey Top - Black | Single Jersey/Modal Lycra + black | Lab dip expected 24/02, delayed to 27/02, Rejected 27/02 (lab dip sent on wrong fabric) Revised lab dip expected 02/03, received 07/03, Approved 07/03 Yarn dispacthed: 15/03 dispatch, expected to reach 22/03, knitting 2 days, dyeing 7 days, FOB expected 6/04, Bulk expected 10/04, Bulk received 10/04 | XS-XL | JJ Fabtex | 200 | 2023-04-28 | PP expected date: 27/02/23, delayed to 01/03 Use fabric from drop-1 PP received 01/02, Fitted 02/03, Approved 07/03, PPM pending | 2023-05-05 | 2023-05-06 | Received 14/04/23, Size- S
SS23/WA/J421/Drop 5 | Longline Kimono - Black & Grey | 100% cotton dobby+ black and grey heart | FOB expected 24/02 Approved on 27/02 Bulk received 1500 mtrs Balance fabric expected by 5/04 | S-M, L-XL | Think stitch | 200 | 2023-04-28 | OG sample sent on: 13/02/23 Fit sample received date: 22/02, Change in style, new pattern and style handed over on 1/03. Fit cum PPS expected date: 16/03, delayed to 20/03, Fitted 21/03, Approved 24/03, PPM pending | 2023-05-01 | 2023-05-03 | Received on 27/03, Size- S-M
SS23/WA/T735/Drop 5 | Tranquila Camisole - Ivory & Black | Cupro Modal + Ivory and black Pond print | S/o received 21/02 Approved for everything except for black color FOB expected date 25/03 Bulk inhouse 01/04 | XS-XL | XLNC | 200 | 2023-04-28 | OG sample sent on: NA PP expected date: 20/03, Fitted 21/03, Approved 23/03, PPM pending | 2023-04-28 | 2023-05-01 | Received on 27/03, Size- S
SS23/WA/T736/Drop 5 | Tranquila Top - Black & Grey | 100% cotton dobby+ black and grey heart | FOB expected 24/02 Approved on 27/02 Bulk received 1500 mtrs Balance fabric expected by 5/04 | S-M, L-XL | Think stitch | 250 | 2023-04-28 | PP received 3/08, Fitted 6/03, Approved 11/03, PPM Pending | 2023-04-22 | 2023-04-25 | Received on 27/03, Size- S-M
SS23/WA/T738/Drop 5 | Gathered Jersey Top - Ivory | Single Jersey/Modal Lycra + Ivory | Lab dip approved on 21/02 Yarn dispacthed: 15/03 dispatch, expected to reach 22/03, knitting 2 days, dyeing 7 days, FOB expected 6/04, Bulk expected 10/04, Bulk received 10/04 | XS-XL | JJ Fabtex | 200 | 2023-04-28 | PP expected date: End of march | 2023-05-05 | 2023-05-06 | Received 14/04/23, Size- S
SS23/WA/D735/Drop 5 | V-neck Strappy Dress - Multi Color | Cupro Modal + Banana Palm print | TS: Submision 1 - rejected 9/02 Submission 2 - rejected 16/02 3rd expected by 24/02, approved 27/02 approved except for bird color 4th expected 28/02, Approved 01/03 FOB by 16/03, delayed to 21/03 Bulk FOB received 21/03, bulk 25/03 Bulk inhouse by 03/04 | XS-XL | XLNC | 300 | 2023-04-28 | OG sample sent on: NA PP expected date: 24/03/23, delayed to 28/03, received 29/03, Fitted 30/03, Not approved 31/03 (Side seam falling forward, adopted pattern revised by tech team ), Revised PP expected date- 05/04, Approved on 06/04 | 2023-05-05 | 2023-05-08 | Received on 13-04-23, Size- S
SS23/WA/D736/Drop 5 | Soup Dress - Black & Grey | 100% cotton dobby+ black and grey heart | FOB expected 24/02 Approved on 27/02 Bulk received 1500 mtrs Balance fabric expected by 5/04 | XS-XL | Think stitch | 250 | 2023-04-28 | OG sample sent on: 13/02/23 Fit sample expected date: 27/02, Fitted 23/02, Approved 27/02 PP sample expected date: 10/03, fitted and approved 14/03, PPM Pending | 2023-04-22 | 2023-04-25 | Received 20/03, Size S
SS23/WA/D737/Drop 5 | Serene Dress - Multi Color | Cupro Modal + Ivory and Black stripes | Bulk delivered S/off Approved on 13/02, FOB expected by 27/02 FOB Inhouse Bulk inhouse | FS | Think stitch | 250 | 2023-04-28 | OG sample sent on: NA Fit sample expected date: 28/02, fitted 28/02, Approved 03/03 PP sample received date: 22/03, fitted 23/03, Approved 24/03, PPM pending | 2023-04-25 | 2023-04-28 | Received on 27/03, Size- FS
SS23/WA/K520/Drop 5 | Soup Kurta - Ivory & Black | Cupro Modal + Ivory and black Pond print | S/o received 21/02 Approved for everything except for black color FOB expected date 25/03 Bulk inhouse 01/04 | XS-XL | XLNC | 280 | 2023-04-28 | OG sample sent on: 07/02/23 Fit sample expected date: 22/02/23, delayed to 23/02, Fitted 28/02, Approved 03/03 PP expected date: 20/03 with shell fabric cord, Fitted 21/03, Approved 23/03, PPM Pending | 2023-04-28 | 2023-05-01 | Received on 27/03, Size- S
SS23/WA/K521/Drop 5 | Konkan Kaftan - Ivory & Black | Cupro Modal + Ivory and black Pond print | S/o received 21/02 Approved for everything except for black color FOB expected date 25/03 Bulk inhouse 01/04 | FS | XLNC | 200 | 2023-04-28 | OG sample sent on: 07/02/23 Fit sample expected date: 22/02/23, delayed to 23/02, Fitted 28/02, Approved 03/03 PP expected date: 20/03, Fitted 21/03, Approved 22/03, PPM Pending | 2023-04-28 | 2023-05-01 | Received on 27/03, Size- S
SS23/WA/K522/Drop 5 | Duck Kaftan - Black & Grey | 100% cotton dobby+ black and grey heart | FOB expected 24/02 Approved on 27/02 Bulk received 1500 mtrs | FS | Think stitch | 280 | 2023-04-28 | OG sample sent on: 13/02/23 Fit sample expected date: 21/02, Fitted 21/02 Approved 27/02, PP sample expceted date: 13/03, received 14/03, fitted 16/03, Approved 17/03, PPM pending | 2023-04-26 | 2023-04-28 | Received 23/03, Size FS
SS23/WA/K523/Drop 5 | Pacific Kaftan - Multi Color | Cupro Modal + Banana Palm print | TS: Submision 1 - rejected 9/02 Submission 2 - rejected 16/02 3rd expected by 24/02, approved except for bird color 4th expected 28/02, Approved 01/03 FOB by 16/03 FOB Inhouse Bulk inhouse date: 03/04 | FS | Think stitch | 250 | 2023-04-28 | OG sample sent on: 13/02/23 Fit sample expected date: 28/02, Fitted 23/02, Approved 27/02 PP sample expected date: 22/03, Fitted 28/03, Approved 28/03, PPM pending | 2023-05-01 | 2023-05-03 | Received 31/03, Size- FS
SS23/WA/K524/Drop 5 | Ocean Kaftan - Ivory & Black | Cupro Modal + Ivory and Black stripes | Bulk delivered S/off Approved on 13/02, FOB expected by 27/02 FOB Inhouse Bulk inhouse | FS | Think stitch | 200 | 2023-04-28 | OG sample sent on: 13/02/23 Fit sample expected date: 28/02, Fitted 28/02,Approved 02/03 PP sample received 14/03, fitted 16/03, Approved 20/03, PPM pending | 2023-05-01 | 2023-05-03 | Received on 31/03, Size- FS
SS23/WA/K525/Drop 5 | Sand Kaftan - Black | Single Jersey/Modal Lycra + black | Lab dip expected 24/02, delayed to 27/02, Rejected 27/02 (lab dip sent on wrong fabric) Revised lab dip expected 02/03, received 07/03, Approved 07/03 Yarn dispacthed: 15/03 dispatch, expected to reach 22/03, knitting 2 days, dyeing 7 days, FOB expected 6/04, Bulk expected 10/04 | FS | JJ Fabtex | 180 | 2023-04-28 | OG sample sent on: 21/02/23 Fit sample expected date: 27/02/23, Fitted 28/02 Approved 02/03 PP sample received on 16/03, Fitted 21/03, Not approved 23/03 due to navy neckline, workmenship, length and sides needs to be decreased, Revised PP expected date 08/04, Mock expected 11/04, Revised PP expected date- 14/04, delayed to 17/04 | 2023-05-05 | 2023-05-06
SS23/WA/B470/Drop 5 | Nova Pants - Black & Grey | 100% cotton dobby+ black and grey heart | FOB expected 24/02 Approved on 27/02 Bulk received 1500 mtrs | XS-XL | Think stitch | 300 | 2023-04-28 | OG sample sent on: NA Fit sample expected date: 22/02, Fitted 23/02, Approved 28/02 PP expected date 07/03, PP fitted 09/03, Approved 13/03, PPM Pending | 2023-04-27 | 2023-05-01 | Received 20/03, Size S
SS23/WA/B471/Drop 5 | Uneven Hem Pants - Multi Color | Cupro Modal + Banana Palm print | TS: Submision 1 - rejected 9/02 Submission 2 - rejected 16/02 3rd expected by 24/02, received 27/02, approved except for bird color 4th expected 28/02, Approved 01/03 FOB by 16/03 FOB inhouse Bulk inhouse date: 03/04 | XS-XL | Think stitch | 250 | 2023-04-28 | OG sample sent on: NA Fit sample expected date: 22/02, Fitted 21/02, Approved 27/02 PP sample received: 22/03, Fitted 23/03, Approved 24/03, PPM pending | 2023-04-29 | 2023-05-01 | Received 28/03, Size S
SS23/WA/B472/Drop 5 | Celeste Pyjamas - Ivory & Black | Cupro Modal + Ivory and Black stripes | Bulk delivered S/off Approved on 13/02, FOB expected by 27/02 FOB Inhouse Bulk inhouse | XS-XL | Think stitch | 250 | 2023-04-28 | PP expected date: 15/03, received 16/03, Fitted and Approved 23/03, PPM pending | 2023-04-21 | 2023-04-25 | Received on 27/03, Size-S
SS23/WA/B473/Drop 5 | Pull-on Pants Black | Single Jersey/Viscose Lycra + black | Bulk in house | XS-XL | SKI | 286 | 2023-04-10 | OG sample sent on: 07/02/23 Fit sample received 07/02/23, Fitted 07/02, Approved 13/02 PP expected: 20/02/23, Fitted 21/02, Approved 23/02, PPM done 07/03. FI done on 31/03 failed, re offered 3/04 | 2023-03-31 | 2023-04-10 | Received on 22/03, Size- Small
SS23/WA/J420/Drop 5 | Celeste Kimono - Multi Color | Cupro Modal + Banana Palm print | TS: Submision 1 - rejected 9/02 Submission 2 - rejected 16/02 3rd expected by 24/02, approved except for bird color 4th expected 28/02, Approved 01/03 FOB by 16/03, delayed to 21/03 Bulk FOB received 21/03, bulk 25/03 Bulk inhouse by 03/04 | S-M, L-XL | XLNC | 200 | 2023-04-28 | OG sample sent on: NA PP expected date: 24/03/23, received 27/03, fitted 28/03, Approved 29/03, PPM pending | 2023-04-28 | 2023-05-01 | Received on 06/04, Size: S-M
SS23/WA/SA40/Drop 2 | Sandbar Sarong - Multi Color | Cupro Modal + Banana Palm print | S/off received 22/02/23 Comments shared 27/02 Revised s/o received 03/03 Approved on 06/03 Bulk by 22/03 | FS | In house | 180 | 2023-04-28 | PP Approved 24/03 Bulk in house - 24/03 | 2023-04-26 | 2023-04-29 | Received on 24/03
SS23/WA/SA41/Drop 2 | Forestry Sarong - Ivory & Black | Cupro Modal + Ivory and black Pond print | S/off received 22/02/23 Comments shared 27/02 Revised s/o received 03/03 Approved on 06/03 Bulk by 22/03 | FS | In house | 180 | 2023-04-28 | PP Approved 24/03 Bulk in house - 24/03 | 2023-04-26 | 2023-04-29 | Received on 24/03
SS23/WA/SA42/Drop 2 | Porch Sarong - Ochre & Grey | Cupro Modal | S/off received 22/02/23 Comments shared 27/02 Revised s/o received 03/03 Approved on 06/03 Bulk by 22/03 | FS | In house | 180 | 2023-04-28 |  | 2023-04-26 | 2023-04-29 | Received
SS23/WA/SA43/Drop 2 | All Hearts Sarong - Ivory & Black | Cupro Modal | S/o received 03/03 Approved on 06/03 Bulk by 22/03 | FS | In house | 180 | 2023-04-28 | OG sample sent on: NA Fit sample expected date: | 2023-04-26 | 2023-04-29 | Received on 24/03
SS22/WA B 217/Drop 4 | Nova Pants - Beige & Black | 100% Cotton French Terry+ Beige and Black stripes |  | XS-XL Sonal : Can we add 2xl and 3 xl here ? | JJ Fabtex | 200 | 2023-05-15 | OG sample sent on: NA Fit sample expected date: 14/03, Fitted 16/03, Approved 18/03, Approved 21/03 PP sample expected date: 27/03 delayed due to eyelet, delayed to 30/03, delayed to 03/04, Fitted 04/04, Approved 05/04, PPM pending | 2023-05-05 | 2023-05-06 | /
SS22/WA/T324/Drop 4 | Triumph Top - Beige & Black | 100% Cotton French Terry+ Beige and Black stripes |  | FS | JJ Fabtex | 150 | 2023-04-28 | OG sample sent on: NA PP sample expected date: 02/03, delayed to 06/03, fitted 06/03, Approved | 2023-05-05 | 2023-05-06 | NA - Reorder - Give NB code Expected 14-04-23
SS22/WA/T324/Drop 4 | Triumph Top - Beige & Black | 100% Cotton French Terry+ Beige and Black stripes | Stock Fabric - dispatched 21/03 | FS | JJ Fabtex | 225 | 2023-05-15 | OG sample sent on: 17/03/23 PP sample approved on: 20/03/23 PPM Pending | 2023-05-05 | 2023-05-06 | NA - Reorder - Give NB code Expected 14-04-23
SS22/WA/D 270/Drop 4 | Celeste Kaftan - Black | Cupro Modal + Black | Bulk dispatched on 15/02 Lab dip expected: 28/02, Bulk fabric color ,Approved 10/03 Bulk delivered Bulk inhouse | FS | Think stitch | 250 | 2023-04-28 | PP sample expected date: 13/03, Fitted 14/03, Approved 15/03, PPM Pending | 2023-04-25 | 2023-04-28 | Received 23/03, Size FS
SS22/WA B 211/Drop 4 | Serena Joggers - Black | Cupro Modal + Black | Bulk dispatched on 15/02 Lab dip expected: 28/02, Bulk fabric color, Approved 10/03 Bulk delivered Bulk inhouse | S-M, L-XL | Think stitch | 200 | 2023-04-28 | PP sample expected date: 13/03, Fitted 14/03, Approved 15/03, PPM Pending | 2023-04-20 | 2023-04-25 | Received 23/03, Size S-M
SS23/WA/K451/Drop 5 | Nisarg Kurta - Charcoal | Y/D Cotton Linen + Charcoal Stripes | Dispatched 22/03 | XS-3XL | Stitch9 | 250 | 31st March | PP Approved 21/03, PPM pending | 2023-04-21 | 2023-04-25 | Received 23/03, Size S
SS23/WA/B441/Drop 5 | Yoka Trousers - Charcoal | Y/D Cotton Linen + Charcoal Stripes | Dispatched 22/03 | XS-3XL | Stitch9 | 400 | 31st March | PP received 22/03, fitted 23/03 Approved 24/03, PPM pending | 2023-04-24 | 2023-04-25 | Received 24/03, Size S
SS23/WA/J370/Drop 5 | Kep Overlay - Charcoal | Y/D Cotton Linen + Charcoal Stripes | Dispatched 22/03 | S-M L-XL | Stitch9 | 180 | 31st March | PP Approved 21/03, PPM pending | 2023-04-23 | 2023-04-25 | Received 23/03, Size S

## Drop 5 serenity
Categories | Style Number | Description | Fabrics | Sizes | Qty | Final Fty | Development Status | OG PO Delivery date | Fit Status | GPT report number | F/I Date | Delivery Date | GRN | Vendor pp ETA
Tops & Shirts | SS23/WA/T720/Drop 4 | Flare Panelled Shirt | Chanderi + Marbling Print 100% Organic Cotton Voile 92/104 + Coral Peony Print 100% cotton voile 80's + ivory RFD | XS-XL | 250 | ThinkStitch |  | 2023-05-15 | PP Approved 19 Apr |  | 2023-05-25 | 2023-05-26 | 2023-05-29 | Shell in Cutting Trim Fabric awaited PP ETA 4th April | TNA Swati
Tops & Shirts | SS23/WA/T721/Drop 4 | Strappy Top | Viscose Linen + Natural | XS-XL | 180 | ThinkStitch |  | 2023-04-30 | Wrong construction Fit Reject 28 MAr Revised fit Recd- 8th April Fit Approved 11 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | In contact with Siraj ji for construction | Lapis- Pending
Tops & Shirts | SS23/WA/T722/Drop 4 | Mandarin Collar Shirt | 100% Organic Cotton Voile 92/104 + Small Botanical print 100% Organic Cotton Voile 92/104 + Coral Peony Print | XS-3XL | 250 | Lapis |  | 2023-04-30 | Fit Approved 06-Mar PP Approved 06 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | ETA 5th april | ThinkStitch - Pending
Tops & Shirts | SS23/WA/T723/Drop 4 | High-low Hem Shirt | 100% Cotton Voile 92/104 + Brown Shibori 100% Cotton Voile 92/104 + Small Botanical print | XS-3XL | 250 | XLNC |  | 2023-05-15 | Fit Approved 04-Mar PP fit 4 April PP Approved 05 Apr |  | 2023-05-25 | 2023-05-26 | 2023-05-29 | ETA 3rd April | XLNC
Tops & Shirts | SS23/WA/T724/Drop 4 | Sleeveless Flared Shirt | 100% Organic Cotton Voile 92/104 + Ivory Peony Print 100% Organic Cotton Voile 92/104 + Coral Peony Print | XS-XL | 220 | Swati |  | 2023-04-30 | Fit Approved 17-Mar PP fit 4 April PP Approved 05 April |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | In Cutting ETA 4th April | Inhouse
Dresses & Jumpsuits | SS23/WA/D720/Drop 4 | Shirt Dress | Chanderi + Marbling Print 100% Organic Cotton Voile 92/104 + Coral Peony Print 100% cotton voile 80's + ivory RFD 100% cotton voile 80's + ivory RFD | XS-XL | 250 | ThinkStitch |  | 2023-05-15 | Fit Approved 01-Mar PP Recd 8th April PP Reject 12 Apr |  | 2023-05-25 | 2023-05-26 | 2023-05-29 | Shell in Cutting Trim Fabric awaited PP ETA 4th April | lapis- fabric pending
Dresses & Jumpsuits | SS23/WA/D722/Drop 4 | Low-back Strappy Dress | 100% Organic Cotton Voile 92/104 + Coral Peony Print 1. 100% cotton voile 80s + DTM to shell | XS-XL | 300 | XLNC |  | 2023-04-30 | Fit approved 01 mar Issue in Fitting, Kamal email 17 Mar Approval Updated on 31 Mar PP Reject 17 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | revised fit sent today | XLNC- Monday shibori
Dresses & Jumpsuits | SS23/WA/D723/Drop 4 | V-neck Strappy Dress | 100% Organic Cotton Voile 92/104 + Ivory Peony Print 100% Organic Cotton Voile 92/104 + Coral Peony Print | XS-XL | 350 | Swati |  | 2023-04-30 | Fit approved 16 Mar PP Approved 08 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | In Cutting ETA 4th April | Swati- Fabric pending
Dresses & Jumpsuits | SS23/WA/D724/Drop 4 | Button Front Dress | 100% Linen + Beige with rose emb leaves 100% Organic Cotton Voile 92/104 + Coral Peony Print 100% cotton voile 80s + dtm to shell | XS-XL | 300 | Inhouse |  | 2023-04-30 | PP Approved 01 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20
Kurtas & Tunics | SS23/WA/K500/Drop 4 | Shawl Collar Kaftan | Chanderi + Marbling Print 100% Organic Cotton Voile 92/104 + Coral Peony Print | FS | 280 | ThinkStitch |  | 2023-05-15 | Fit approved 28 feb PP Approved 08 Apr |  | 2023-05-25 | 2023-05-26 | 2023-05-29 | Shell in Cutting Trim Fabric awaited PP ETA 4th April
Kurtas & Tunics | SS23/WA/K501/Drop 4 | Sleeveless High Neck Kurta | Viscose Linen + Natural 100% Organic Cotton Voile 92/104 + Coral Peony Print | XS-3XL | 250 | ThinkStitch |  | 2023-04-30 | fit approved 06 mar PP Recd 04th Mar PP Approved 05 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | Shell in Cutting Trim Fabric awaited PP ETA 4th April
Kurtas & Tunics | SS23/WA/K502/Drop 4 | Boxy Kurta | 100% Organic Cotton Voile 92/104 + Big Botanical print 100% Organic Cotton Voile 92/104 + Coral Peony Print | XS-XL | 220 | Lapis |  | 2023-04-30 | fit approved 11 March PP Approved 08 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | ETA 5th april
Kurtas & Tunics | SS23/WA/K503/Drop 4 | Sleeveless gathered kurta | 100% Cotton Voile 92/104 + Brown Shibori 100% Cotton Voile 92/104+ Small Botanical print | XS-3XL | 250 | XLNC |  | 2023-05-15 | Fit approved 06 Mar PP Recd 04th Mar PP Approved 05 Aprr |  | 2023-05-25 | 2023-05-26 | 2023-05-29 | ETA 3rd April
Kurtas & Tunics | SS23/WA/K505/Drop 4 | Pintuck Kurta | 100% Organic Cotton Voile 92/104 + Coral Peony Print 100% Organic Cotton Voile 92/104 + Ivory Peony Print | XS-3XL | 250 | XLNC | UPCHARGE OF RS 200/ DUE TO TECH PACK MISSING PIN TUCKS IN BACK BODY | 2023-04-30 | Fit Approved 24 Mar PP Approved 17 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | ETA 3rd April
Kurtas & Tunics | SS23/WA/K506/Drop 4 | Basic Longlength Kurta | 100% Organic Cotton Voile 92/104 + Ivory Peony Print 100% Organic Cotton Voile 92/104 + Coral Peony Print | XS-3XL | 250 | Swati |  | 2023-04-30 | Fit approved 15 Mar PP Approved 05 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | In Cutting ETA 4th April
Bottoms | SS23/WA/B450/Drop 4 | Narrow Belted Trousers | Viscose Linen + Natural 100% Cotton Voile 92/104 + Small Botanical Print | 26-34 |  | ThinkStitch |  | 2023-04-30 | Fit Approved 04-Mar PP Approved 08 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | Shell in Cutting Trim Fabric awaited PP ETA 4th April
Bottoms | SS23/WA/B451/Drop 4 | Basic Pyjama | 100% Organic Cotton Voile 92/104 + Small Botanical print | XS-3XL | 400 | Lapis |  | 2023-04-30 | Fit approved 02 Mar PP Approved 08 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | ETA 5th april
Bottoms | SS23/WA/B452/Drop 4 | Paperbag Waist Pants | 100% Cotton Voile 92/104 + Brown Shibori | XS-XL |  | XLNC |  | 2023-05-15 | Fit approved 02 Mar PP Approved 06 Apr |  | 2023-05-25 | 2023-05-26 | 2023-05-29 | ETA 3rd April
Bottoms | SS23/WA/B453/Drop 4 | Puff Pants | 100% Organic Cotton Voile 92/104 + Coral Peony Print | XS-3XL |  | XLNC |  | 2023-04-30 | Fit approved 15 Mar PP Approved 11 Apr |  | 2023-05-15 | 2023-05-17 | 2023-05-20 | Fit will be sent back from tulsi today
Bottoms | SS 22/WA B 216/Drop 4 | Serene Pants - Ivory | 100% Cotton Kora + Ivory (RFD) | XS- 3XL |  | ThinkStitch |  | 2023-04-30 | Fit Reject 07 Mar PP approved 15 Mar |  | 2023-05-15 | 2023-05-17 | 2023-05-20
Jackets & Overlays | SS23/WA/J380/Drop 3 | V-neck Overlay | Chanderi + Marbling Print 100% Organic Cotton Voile 92/104 + Coral Peony Print | XS-XL |  | ThinkStitch |  | 2023-05-15 | Fit Approved 04-Mar PP recd 8th April PP Approved 12 Apr |  | 2023-05-25 | 2023-05-26 | 2023-05-29 | Shell in Cutting Trim Fabric awaited PP ETA 4th April
Formulas:
Delivery Date = [F/I Date]+1
GRN = [Delivery Date]+3

## Nico Sports
Categories | Style Number | Description | Fabrics | Sizes | Qty | Final Fty | Bulk Fabric | Development Status | OG PO Delivery date | Fit Status | F/I Date | Vendor pp ETA |  |  |  | Photoshoot Samples
MW | NSM T0015 A | Rise Crewneck T-shirt - Dark green | 57% cotton 38% modal 5% elastane Single jersey 220 gsm | S-XL | 200 | JJ FAB | FOB sent for approval - 24/3/23. FOB APPROVED - 27/3/23 | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30 | 2023-03-30 | Rib - 27/3/23 | A/w + HD - 28/3/23
MW | NSM T0015 B | Rise Crewneck T-shirt - Ochre | 57% cotton 38% modal 5% elastane Single jersey 220 gsm | S-XL | 200 | JJ FAB | FOB ETA - 30/3/23 FOB OK | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30 |  |  | A/w Closed
MW | NSM T0015 C | Rise Crewneck T-shirt - White | 57% cotton 38% modal 5% elastane Single jersey 220 gsm | S-XL | 200 | JJ FAB | FOB ETA - 30/3/23 | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30 |  |  |  | HOLD
MW | NSM T0015 D | Rise Crewneck T-shirt - Coral | 57% cotton 38% modal 5% elastane Single jersey 220 gsm | S-XL | 200 | JJ FAB | FOB ETA - 30/3/23 FOB Approved - 28/3 | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30 |  |  | A/w Closed
MW | NSM T0015 E | Rise Crewneck T-shirt - Navy | 57% cotton 38% modal 5% elastane Single jersey 220 gsm | S-XL | 200 | JJ FAB | FOB ETA - 30/3/23 FOB Approved - 3/4 | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30
MW | NSM T0017 A | Birdie Polo T-shirt - White | 58% cotton 38% modal 4% elastane pique 240 gsm | S-XL | 200 | JJ FAB | FOB ETA - 30/3/23 FOB OK | Labdip Approved. Final Approval on FOB | 2023-05-10 | Fit Closed | 2023-04-30 | PP Recd | Flatknit+ Mock - 24/03 |  | HOLD | 18/4
MW | NSM T0017 B | Birdie Polo T-shirt - Coral | 58% cotton 38% modal 4% elastane pique 240 gsm | S-XL | 200 | JJ FAB | FOB ETA - 30/3/23 FOB OK | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30 | PP Recd | Flatknit+ Mock - 24/03 | A/W Closed |  | 18/4
MW | NSM T0017 C | Birdie Polo T-shirt - Dark green | 58% cotton 38% modal 4% elastane pique 240 gsm | S-XL | 200 | JJ FAB | FOB ETA - ??/4/23 | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30 |  | Flatknit+ Mock - 24/03
MW | NSM T0018 A | Volley Polo T-shirt - Navy | 58% cotton 38% modal 4% elastane pique 240 gsm | S-XL | 200 | JJ FAB | FOB ETA - 10/4/23 FOB - OK | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30 | 15/4/23 | Flatknit+ Mock - 24/03 | A/W Closed
MW | NSM T0018 B | Volley Polo T-shirt - Ochre | 58% cotton 38% modal 4% elastane pique 240 gsm | S-XL | 200 | JJ FAB | FOB ETA - 30/3/23 FOB APPROVED | Labdip Approved. | 2023-05-10 | Fit Closed | 2023-04-30 | 17/4 | Flatknit+ Mock - 24/03 |  |  | 17/4
Latest Bulk I/h by 5/4/23
[5 empty] | 2000 | 10